## Sheet1
WILKINS DEVELOPMENT BUDGET
HARD COSTS:
| DESIGN/BUILD GMP | 22901191.26
| OWNER'S CONTINGENCY ON NEW CONSTRUCTION - 5% | 1145059.563
| GENERATOR | 200000
| SOLAR - IF COST/BENEFIT ANALYSIS CONFIRMS | 200000
| MOVE 4TH GRADE PORTABLES FOR CONSTRUCTION PURPOSES | 50000
| AUDIO/VISUAL | 100000
| SITE SECURITY & CONSULTING FOR PROJECT | 100000
| Total: | 24696250.823
WILKINS UPDATES TO MEET CODE & REFRESH BUILDING - ORIGINAL SCOPE
Exterior
| Repair/remove rotted trim board and cover with metal around building | 75000 | SUMMER 2026
| Exterior shed on the backside of MPR, siding repairs (snow blower, gas, ladders, etc. stored inside) | 10000 | SUMMER 2026
| Exterior caulking (expansion joints, windows, etc.) - Under Aaron's Management!!! | 75000 | SUMMER 2026
| Windows fair condition but replacement of weights and springs 30% | 30000 | SUMMER 2026
| Additional paving repairs | 30000 | SUMMER 2026
Mech/Electrical
| Remove the Federal Pacific panels. We need to look at the service as well and confirm if FP but I don't believe the service gear had the same issue as their panels ASSUME 2 PANELS AT $10K EACH | 20000 | SUMMER 2026
| Mechanical improvements Misc. | 20000 | SUMMER 2026
Plumbing
| Replace kitchen and boiler room water heater | 5000 | SUMMER 2026
| Kitchen dishwasher system (Krystal may be replacing this already this summer) | 5000 | SUMMER 2026
Fire Protection
| Glycol in the sprinkler system. I am working on this to add an NFPA rated solution. Here's what I see below, $4200 for 55 gallon drum: PER ROGER PRESTON NOT NEEDED NOW COVERED IN OPERATIONS BUDGET | 0 | SUMMER 2026
https://elaraeng.com/nfpa-driven-sprinkler-system-antifreeze-replacement-required-september-30-2022/
Misc.
| Asbestos abatement as shown to be existing under new VCT throughout the building. As mentioned we are meeting the AHERA requirements with recurring inspections. Off the cuff # from reputable contractor I've used based on emailed plans | 275000 | SUMMER 2027
| Replace all floor tiles with new VCT after abatement is complete 55,000 * $6 (or concrete polish) | 330000 | SUMMER 2027 TO SPRING 2028'
| Replace all ACT ceiling tiles 55,000 * $6 (SOME OF THIS COST COULD BE INCLUDED IN $450K COST BELOW) | 330000 | SUMMER 2027 TO SPRING 2028'
| Re-build new front office area adjacent to entrance doors, including principal, asst principal & admin. (SHOULD BE ABLE TO INCLUDED IN $450K # BELOW) | 100000 | SUMMER 2027 TO SPRING 2028'
| Replace light fixtures in classroom ceilings (MAY BE REDUCED FROM EVERSOURCE REBATE) | 300000 | SUMMER 2027 TO SPRING 2028'
| Cubbies & Coat Hangers to organize kid's belongings & Misc Finish Carpentry Work to Enhance Spaces | 100000 | SUMMER 2027 TO SPRING 2028'
| Repaint Corridors & New Partitioned Areas | 250000 | SUMMER 2027 TO SPRING 2028'
| Move Classroom materials to new Addition (SHOULD BE LESS - MAY BE PARTIALLY COVERED IN OPERATIONS BUDGET) | 100000 | SUMMER 2027 TO SPRING 2028'
| ADA compliant bathrooms and access | 300000 | SUMMER 2027 TO SPRING 2028'
| SUBTOTAL ORIGINAL SCOPE | 2355000
15 YEAR LOOK AHEAD SCOPE ABOVE ORIGINAL $19.3M PLAN PER FACILITY MANAGER
| Allowance to partition off former classrooms into interventionist rooms, case rooms etc per Principal's direction Summer 2027 after addition is complete (MAY BE REDUCED BASED ON PROPOSED LAYOUTS) | 450000 | SUMMER 2027 TO SPRING 2028'
| Replace Existing Roofs on Building - assume 70,000 sf * $11/sf | 770000 | SUMMER 2027 TO SPRING 2028'
| Replace Rooftop Units to Include Cooling Coil | 250000 | SUMMER 2027 TO SPRING 2028'
| Inspect and clean all ductwork runs | 100000 | SUMMER 2027 TO SPRING 2028'
| Run new ductwork to partitioned spaces | 100000 | SUMMER 2027 TO SPRING 2028'
| New Electrical wiring allowance 55000*10 | 550000 | SUMMER 2027 TO SPRING 2028'
| New Plumbing Allowance 200000 | 200000 | SUMMER 2027 TO SPRING 2028'
| Replace sprinkler piping allowance 55000*10 (MAY ONLY NEED NEW HEADS) | 550000 | SUMMER 2027 TO SPRING 2028'
| New insulation above ceilings (MAY BE REDUCED WITH EVERSOURCE REBATE) | 250000 | SUMMER 2027 TO SPRING 2028'
| New fire taped 5/8" sheetrock ceilings 45000*5 | 225000 | SUMMER 2027 TO SPRING 2028'
| New Building Management System (MAY BE REDUCED WITH EVERSOURCE REBATE) | 150000 | SUMMER 2027 TO SPRING 2028'
| New Fire Alarm Control Panel & Devices | 250000 | SUMMER 2027 TO SPRING 2028'
| Misc Tie-in to Addition | 100000 | SUMMER 2027 TO SPRING 2028'
| Misc. Additional Work | 250000 | SUMMER 2027 TO SPRING 2028'
Yellow - new work not included in Original Plan
| Subtotal: | 6550000 | 129.1175
| Contingency - 15% | 982500
| GC Overhead & Profit - 15% | 982500 | GOAL WILL BE FOR AS MUCH WORK AS POSSIBLE TO BE MANAGED BY SAU DISTRICT PERSONNEL TO REDUCE GC/ARCH MARKUP
| Architectural Fee - 10% | 655000
| Total: | 9170000 | 180.7645
SOFT COSTS:
| OWNER'S REP | 350000
| CIVIL/SITE ENGINEER | 125000
| 3RD PARTY CONSULTANTS - SOIL, CONCRETE, STEEL, FAÇADE ETC | 125000
| LEGAL | 150000
| BUILDER'S RISK INSURANCE (Included in Design Build GMP) | 0
| SOFT COST CONTINGENCY | 300000
| FF&E | 575000
| Soft Costs Total: | 1625000
TOTAL COSTS RENOVATE AND EXPAND: |  | 35491250.823
| CONTINGENCY BETWEEN BOND AMOUNT AND FORECASTED TOTAL COST: | 1508749.177
| TOTAL BOND: | 37000000
| TOTAL CONTINGENCIES INCLUDED WITHIN BUDGET: | 4800941.71
| TOTAL % CONTINGENCY FOR PROJECT: | 13.53%

## Sheet2
HARD COSTS: |  | 47500 | $/SF
| DESIGN/BUILD GMP - NEW BUILD | 22901191.26 | 482.1303
| OWNER'S CONTINGENCY - 10% | 1145059.563 | 24.1065
| MOVE ONE 4TH GRADE PORTABLE FOR CONSTRUCTION PURPOSES | 50000 | 1.0526
| AUDIO/VISUAL | 100000 | 2.1053
| SITE SECURITY & CONSULTING FOR PROJECT | 100000 | 2.1053
0
| Total: | 24296250.823 | 511.5
WILKINS UPDATES TO MEET CODE & REFRESH BUILDING |  |  | 50729
| SUBTOTAL | 6550000 | 129.1175
| Contingency - 15% | 982500 | 19.3676
| GC Overhead & Profit - 15% | 982500 | 19.3676
| Architectural Fee - 10% | 655000 | 12.9117
| TOTAL: | 9170000 | 180.7645
SOFT COSTS:
| OWNER'S REP | 300000
| CIVIL/SITE ENGINEER | 75000
| 3RD PARTY CONSULTANTS - SOIL, CONCRETE, STEEL, FAÇADE ETC | 100000
| LEGAL | 150000
| BUILDER'S RISK INSURANCE | 400000
| SOFT COST CONTINGENCY | 250000
| FF&E | 575000
| Soft Costs Total: | 1625000
TOTAL COSTS PHASE #1 with Wilkins Code & Refresh Work: |  | 35091250.823